## Product Backlog
PRODUCT BACKLOG
[8 empty] | High | Medium
| SPRINT | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY
| 1 | US1 | As a project manager, I want a clear project roadmap, so I can track progress. | Project Manager | Prepare project timeline, requirement and resource gathering is done. | High
| 1 | US2 | As a frontend developer, I need to design mockups and wireframes. | Frontend Developer | Create UI for Home screen(dashboard, login screen) | Medium
| 1 | US3 | As an admin, I want to manage users. | Backend Developer | Set up version control, build tools, and deployment of backend infrastructure | High
| 2 | US4 | User Authentication | Frontend, Backend | Frontend: Designs UI for Register and Login Page Backend: Implements Data processing and Login API. | High
| 2 | US5 | As an admin, I want to manage users. | Frontend, Backend | Build APIs and admin dashboard UI | High
| 3 | US6 | User can search for travel packages | Backend, Frontend | Build search API and integrate UI | High
| 3 | US7 | Users can filter packages by price, date, etc. | Backend, Frontend | Implement filtering in APIs and UI. | High
| 4 | US8 | Users can book travel packages. | Backend, Frontend | Develop booking API and integrate UI. | High
| 4 | US9 | Users can view their booking history. | Backend, Frontend | Build history API and display UI. | High
| 5 | US10 | Secure payments for bookings. | Backend, Frontend | Integrate payment gateway and design UI. | High
| 6 | US11 | Admins can manage travel packages and view analytics. | Backend, Frontend | Develop CRUD APIs and create analytics UI. | Medium
| 6 | US12 | As an admin, I want to view booking statistics. | Backend, Frontend | Backend develops Analytics API, while Frontend Develops Admin UI for Booking reports | Medium
| 7 | US13 | As a QA tester, I want to test the system for bugs. | QA Tester | Ensure bug-free and efficient system. | Medium
| 7 | US14 | As a developer, I want to optimize system performance. | Backend | Optimize queries and improve API Perfomance | Medium
| 8 | US15 | As a developer, I want to deploy the system to production. | Backend, Frontend | Deploy to production server, ensure final tests are completed. | High
| 8 | US16 | As a project manager, I want to review project progress and gather feedback. | Project Manager | Conduct retrospective, document lessons learned. | Medium
Total Budget
|  |  | Role | Percentage | Monthly Salary | 4 Month Salary | Annual Salary
|  |  | Frontend Developer | 15% | 90000 | 320000 | 1080000
|  |  | Backend Developer 1 | 10% | 60000 | 240000 | 720000
|  |  | Backend Developer 2 | 10% | 60000 | 240000 | 720000
|  |  | UI/UX Designer | 10% | 60000 | 240000 | 720000
|  |  | QA Analyst/Tester | 15% | 90000 | 360000 | 1080000
|  |  | Project Manager | 25% | 150000 | 600000 | 1800000
|  |  | Business Analyst | 15% | 90000 | 360000 | 1080000
|  |  | Miscellaneous | N/A | 25000 | 100000 | N/A
|  |  | Total | 100% | 625000 | 2500000 | 7200000

## Sprint 1
Month 1 Sprint 1 (2 Weeks)
| SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
| 1 | US1 | Initial Setup and Feature Understanding | Project Manager, BA, and Developers | Prepare project timeline, requirement and resource gathering is done. | High | Completed
| 2 | US2 | As a frontend developer, I need to design mockups and wireframes. | Frontend Developer | Create UI for Home screen(dashboard, login screen) | Medium | Completed
| 3 | US3 | As an admin, I want to manage users. | Backend Developer | Set up version control, build tools, and deployment of backend infrastructure | High | Completed
| 4 | US4 | As an Admin I need User Authentication | Frontend, Backend | Frontend: Designs UI for Register and Login Page Backend: Implements Data processing and Login API. | High | Completed
Sprint 1 Budget
|  | Role | Per Sprint Salary | 4 Month Salary | Annual Salary
|  | Frontend Developer | 22500 | 320000 | 1080000
|  | Backend Developer 1 | 15000 | 240000 | 720000
|  | Backend Developer 2 | 15000 | 240000 | 720000
|  | UI/UX Designer | 30000 | 240000 | 720000
|  | QA Analyst/Tester | 22500 | 360000 | 1080000
|  | Project Manager | 37500 | 600000 | 1800000
|  | Business Analyst | 22500 | 360000 | 1080000
|  | Total | 165000 | 2360000 | 7200000

## Sprint 2
Sprint 2 (2 Weeks)
| USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
| US1 | As developer, I need proper user dashboard for easy access. | Developers, QA Analyst, Project Manager | Develop user profile management and dashboard. | High | Completed
| US2 | As a frontend developer, I need to design API's for login purpose | Frontend Developer | Start integrating APIs for login and user data. | Medium | Completed
| US3 | As a Business Analyst, I need the documentation of implemented features | Business Analyst | Prepare documentation for implemented features. | High | Completed
| US4 | User Authentication | Frontend, Backend | Frontend: Designs UI for Register and Login Page Backend: Implements Data processing and Login API. | High | Completed
Sprint 2 Budget
| Role | Per Sprint Salary | 4 Month Salary | Annual Salary
| Frontend Developer | 22500 | 320000 | 1080000
| Backend Developer 1 | 15000 | 240000 | 720000
| Backend Developer 2 | 15000 | 240000 | 720000
| UI/UX Designer | 30000 | 240000 | 720000
| QA Analyst/Tester | 22500 | 360000 | 1080000
| Project Manager | 37500 | 600000 | 1800000
| Business Analyst | 22500 | 360000 | 1080000
| Total | 165000 | 2360000 | 7200000

## Sprint 3
Month 2- Sprint 3
SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
1 | US1 | User can search for travel packages | Frontend Developer, QA Analyst | Implement search functionality for travel packages and destinations. | High | Completed
2 | US2 | Users can filter packages by price, date, etc. | Frontend Developer | Add filters for price range, dates, and destinations. | Medium | Completed
3 | US3 | Finalizing API for beter perfomance | Frontend, Backend Developer | Build API's for for fetching search results and filtering data | High | Completed
4 | US4 | QA will check for accuracy through testing | QA Analyst | Validate search results and filter accuracy for rigorous testing | High | Completed
Sprint 3 Budget
| Role | Per Sprint Salary | Monthly Salary | Annual Salary
| Frontend Developer | 22500 | 320000 | 1080000
| Backend Developer 1 | 15000 | 240000 | 720000
| Backend Developer 2 | 15000 | 240000 | 720000
| UI/UX Designer | 30000 | 240000 | 720000
| QA Analyst/Tester | 22500 | 360000 | 1080000
| Project Manager | 37500 | 600000 | 1800000
| Business Analyst | 22500 | 360000 | 1080000
| Total | 165000 | 2360000 | 7200000

## Sprint 4
Sprint 4 (2 Weeks)
SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
1 | US1 | As an User I need to make bookings | Backend Developer | Building API's for travel booking (Phase-I) | High | Completed
2 | US2 | Users can search for travel bookings in the search bar | Backend Developer | Extending Database schema for bookings | High | Completed
3 | US3 | As an User I need payment gateway to finalize my booking | Frontend Developer, UI/UX Designer, QA | Conducting research for payment gateway | High | Completed
4 | US4 | QA will check for final result after checking | QA Analyst | Validate research analysis and get feedback from QA | High | Completed
Sprint 4 Budget
Role | Per Sprint Salary | Monthly Salary | Annual Salary
Frontend Developer | 22500 | 320000 | 1080000
Backend Developer 1 | 15000 | 240000 | 720000
Backend Developer 2 | 15000 | 240000 | 720000
UI/UX Designer | 30000 | 240000 | 720000
QA Analyst/Tester | 22500 | 360000 | 1080000
Project Manager | 37500 | 600000 | 1800000
Business Analyst | 22500 | 360000 | 1080000
Total | 165000 | 2360000 | 7200000

## Sprint 5
Month 3 Sprint 5
SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
1 | US1 | As an admin I need a secure payment gateway to confirm my transaction | QA, BA, and Developers | Integrate the selected payment gateway into the booking system | High | Completed
2 | US2 | User can safely do payment process in the payment gateway | Frontend Developer | Develop and integrate the frontend payment flow | Medium | Completed
3 | US3 | As an admin, I want to see my booking status | Backend Developer | Update bookings in the database for payment status | High | Completed
Sprint 5 Budget
| Role | Per Sprint Salary | Monthly Salary | Annual Salary
| Frontend Developer | 22500 | 320000 | 1080000
| Backend Developer 1 | 15000 | 240000 | 720000
| Backend Developer 2 | 15000 | 240000 | 720000
| UI/UX Designer | 30000 | 240000 | 720000
| QA Analyst/Tester | 22500 | 360000 | 1080000
| Project Manager | 37500 | 600000 | 1800000
| Business Analyst | 22500 | 360000 | 1080000
| Total | 165000 | 2360000 | 7200000

## Sprint 6
Sprint 6 (2 Weeks)
SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
1 | US1 | As an User I need to manage all my booking history | Project Manager, QA, and Developers | Build booking history module and notification system | High | Completed
2 | US2 | User needs to be Notified via push Sms/email for the booking updates | Frontend Developer, UI/UX Designer | Create Notifications for booking updates | High | Completed
3 | US3 | As an admin, I need clean UI | Backend Developer | Optimize API's for booking history and notifications | Medium | Completed
4 | US4 | QA will check the UI and give feedback | QA, Frontend Developer | Enhanced Booking UI and send for testing to the QA | High | Not Completed
Sprint 6 Budget
Role | Per Sprint Salary | Monthly Salary | Annual Salary
Frontend Developer | 22500 | 320000 | 1080000
Backend Developer 1 | 15000 | 240000 | 720000
Backend Developer 2 | 15000 | 240000 | 720000
UI/UX Designer | 30000 | 240000 | 720000
QA Analyst/Tester | 22500 | 360000 | 1080000
Project Manager | 37500 | 600000 | 1800000
Business Analyst | 22500 | 360000 | 1080000
Total | 165000 | 2360000 | 7200000

## Sprint 7
Month 4 Sprint 7
SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
1 | US1 | As an User I need error free software | Developers, QA, BA | Optimize system performance and fix critical bugs | High | Completed
2 | US2 | As a User I need the software to run on all platforms | Frontend Developer, QA | Ensure application responsiveness across various device platforms | High | Completed
3 | US3 | BA will check the technical documentation after finalizing | BA, QA, Frontend Developer | Update technical and user documentation | High | Not Completed
4 | US4 | QA will run some tests to ensure the software is perfoming well | QA, Frontend, Backend | Preparing for Final launch | High | Not Completed
Sprint 7 Budget
Role | Per Sprint Salary | Monthly Salary | Annual Salary
Frontend Developer | 22500 | 320000 | 1080000
Backend Developer 1 | 15000 | 240000 | 720000
Backend Developer 2 | 15000 | 240000 | 720000
UI/UX Designer | 30000 | 240000 | 720000
QA Analyst/Tester | 22500 | 360000 | 1080000
Project Manager | 37500 | 600000 | 1800000
Business Analyst | 22500 | 360000 | 1080000
Total | 165000 | 2360000 | 7200000

## Sprint 8
Sprint 8
| SR No. | USER STORY ID | USER STORY | ROLE | TASK | PRIORITY | STATUS
| 1 | US1 | QA will test the application post deployment | Project Manager, QA, and Developers | Deployment of software in production environments | High | Completed
| 2 | US2 | QA will test the product for any bugs, issues | BA, Project Manager | Conducting User Acceptance Testing (UAT) for user feedback | Medium | Not Completed
| 3 | US3 | QA will give feedback post testing the software | QA, Developers | Resolve issues identified during UAT | High | Not Completed
| 4 | US4 | User gets the software for working | Frontend, Backend | After verifying all the functionalities the final softwae is released | High | Not Completed
Sprint 8 Budget
|  | Role | Per Sprint Salary | Monthly Salary | Annual Salary
|  | Frontend Developer | 22500 | 320000 | 1080000
|  | Backend Developer 1 | 15000 | 240000 | 720000
|  | Backend Developer 2 | 15000 | 240000 | 720000
|  | UI/UX Designer | 30000 | 240000 | 720000
|  | QA Analyst/Tester | 22500 | 360000 | 1080000
|  | Project Manager | 37500 | 600000 | 1800000
|  | Business Analyst | 22500 | 360000 | 1080000
|  | Total | 165000 | 2360000 | 7200000